## 30-06-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-06-30 | Rajani.I.R | Lab module | 1.Testing on patient management and sample management and testing observations recorded 2. Guidaince given to Harshith to write the test cases | 1 round of testing Completed | Present
2 | 2026-06-30 | Basavaraju N N | Pharma Module | Implemented OTP functionality for email validation, Updated the pharma entity according to the latest changes. | Completed | Present
3 | 2026-06-30 | Moses | Lab module | Packages and Test management | in progress | Present
4 | 2026-06-30 | Shreeraksha | Pharma Module | Worked on Registration Screen in Frontend | In Progress | Present
5 | 2026-06-30 | Sunny Kumar | Lab module | Bug Fixing of Sample management (New UI) | In Progress | Present
6 | 2026-06-30 | Prabhas K S | Pharma Module | Worked on Dashboard Screen in Frontend | in progress | Present
7 | 2026-06-30 | Dipak | Lab Module | Worked on the Super Admin Dashboard Key Performance Indicators.Implemented API integration to fetch Total Labs, Total Admins, Total Desk Users, and Total Technicians from the database. | completed | Present
8 | 2026-06-30 | Somil Merugawar | MarketPlace and Admin | Setup in local and understand flow backned and frontend | in progress | Present
9 | 2026-06-30 | S J Yasshraj Vijayan | Lab Module | Frontend UI and integration of AI in reports. | In progress | Present
10 | 2026-06-30 | Amit Hosmani | Lab Module | UI/UX assistance for Package Management & Test Master | in progress | Present
| 2026-06-30 |  | Inventory Module | SRS update for Compliance Submission, Compliance Status Dashboard, Compliance Correction & Resubmission Use Cases | Completed
| 2026-06-30 |  |  | UI/UX assistance for Super Admin login page | Completed
11 | 2026-06-30 | Archana Jagadish | ISRO | Information gathering about Uttara Kosha | Completed | Present
| 2026-06-30 |  | Lab module | Testing Lab Module | in progress
12 | 2026-06-30 | Roshni |  | Training - UI | in progress | Present
13 | 2026-06-30 | Harshith | Lab module | Training - Testing | in progress | Present

## 1-07-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-01-07 | RAJANI.I.R | Lab Module | 1.Testing of package creation and testing observations recorded. | Completed | Present
|  |  |  | 2.Guidance given to Harshith on Test case writing | In Progress
|  |  | Pharma Module | 1.Test case preparation for account registry page | In Progress
|  |  |  | 2.Study of Inventory SRS v0.4 | In Progress
2 | 2026-01-07 | ROSHNI MOHAN | Training | Training UI - practice on login webpage | Submitted for review | Present
3 | 2026-01-07 | HARSHITH GOWDA G | Training | practice on test cases | completed | Present
4 | 2026-01-07 | S J Yasshraj Vijayan | Lab Module | Package Management UI Screens, bug fixes | completed | Present
|  |  | Lab Module | AI Integration and Report UI | In Progress | Present
5 | 2026-01-07 | Dipak | Lab Module | Implemented backend API integration for the Super Admin Dashboard to dynamically fetch and display Total Tests, Total Revenue, Pending Samples, and Total Reports Generated from the database | Completed | Present
6 | 2026-07-01 | Somil Merugawar | Pharma Aggregater(MarketPlace) | Analyzed the Seller Registration process, understood the Seller Account and OTP verification flow, and reviewed the application's high-level infrastructure and architecture. | In Progress | Present
Tiameds Admin
7 | 2026-01-07 | Ashikjoshi | MarketPlace | 1.Reviewed the Software Requirements Specification (SRS) for the Marketplace module. 2.Discussed the Lab Module features and functional requirements with the Business Analyst (BA) and development team. | In Progress | Present
8 | 2026-01-07 | Basavaraju N N | Pharma Module | Working on user flow API after admin sent for correction. | In Progress | Present
9 | 2026-01-08 | Shreeraksha | Pharma Module | Updated Pharmacy Registration and compliance upload according to new SRS | Completed | Present
10 | 2026-01-07 | Prabhas K S | Pharma Module | worked on API integration for admin flow, dashboard UI | Completed | Present
11 | 2026-01-07 | Moses | Lab module | Designing UI/UX for Test management and References | In Progress | Present
12 | 2026-01-07 | Sunny | Lab module | Bug fixed - 4 1. Auto calculation of Test result input. 2. Edit Test of Test Result. 3. KPIs of Sample Managemnet 4. Test & package view in sample managemnet fixed. | Completed | Present
13 | 2026-01-07 | Archana Jagadish | Lab module | 1. Testing of Lab Management 2. Evaluation of Free Disposable Email address providers for use during testing | Completed | Present
|  |  | ISRO | Uttarakosha requirement gathering
14 | 2026-01-07 | Amit Hosmani | Lab Module | UI/ UX revamp for Test Master Creation | In Progress | Present
|  |  | Pharma Module | SRS update with revamped business logic to onboard healthcare entities, User Login and Dashboard access & Business setup initiation | Completed
|  |  |  | UI/UX assistance revamp for Business Super Admin self registration, user login and dashboard access | In Progress

## 2-07-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-02-07 | Rajani.I.R | Lab Module | 1.Testing report generation of 179 tests and testing observations recorded | Completed | Present
|  |  |  | 2.Retesting of fixed bugs - whichever was pushed to testing environment | Completed
|  |  |  | 3.Support given to Kaveri Hospital in adding new test for tommorrow camp - as directed by Manjunath sir | Completed
2 | 2026-02-07 | Basavaraju N N | Pharma Module | Completed admin correction flow, | Completed | Present
|  |  |  | Updated the registration flow | Completed
|  |  |  | Created endpoint for email verification | Completed
|  |  |  | Updated changes for login | Completed
3 | 2026-02-07 | S J Yasshraj Vijayan | Lab Module | AI Integration in Lab Report | In Progress | Present
|  |  |  | Lab Report UI | In Progress
|  |  |  | Package Management bugs | Completed
|  |  |  | Patient Management bugs | Completed
4 | 2026-02-07 | Harshith Gowda | Training | Done with the learning Test Cases | Completed | Present
5 | 2026-02-07 | Prabhas K S | Pharma Module | Otp component developemnt | Completed | Present
|  |  |  | login and verifyOtp api integration and routing | Completed
6 | 2026-02-07 | Dipak | Lab Module | Implemented backend API integration for the Super Admin Revenue Trend Dashboard to retrieve date-wise revenue data from the database. | Completed | Present
7 | 2026-02-07 | Ashik joshi | Inventory Module | "1.Reviewed the Software Requirements Specification (SRS) for the Inventory module. 2.Discussed the Inventory Module features and functional requirements with the Business Analyst (BA) and UI/UX team." | In Progress | Present
8 | 2026-02-07 | Amit Hosmani | Pharma Module | SRS update with revamped business logic to onboard healthcare entities, User Login and Dashboard access & Business setup initiation with compliance details submission for Single Pharmacy and Chain of Pharmacies | Completed | Present
|  |  |  | UI/UX assistance revamp for Business Super Admin self registration, user login and dashboard access, Business setup initiation wih compliance submission for Single Pharmacy and Chain of Pharmacies | In Progress
9 | 2026-02-07 | Somil Merugawar | AWS CICD ALL PROJECT | Build CI/CD architecture flow documentation and debugged the deployment process. | In Progress | Present
10 | 2026-02-07 | Sunny | Lab module | Bug fixed - 4 1. Error message display. 2. Reference values displayed & discription input changed for different test fixed. Differential count pop up added in CBC report. | Completed | Present
11 | 2026-02-07 | Shreeraksha | Pharma Module | Updated Pharmacy Registration according to new SRS | Completed | Present
12 | 2026-02-07 | Moses | Pharma module | Designing UI/UX for Business Super Admin self registration, user login and dashboard access, Business setup initiation wih compliance submission for Single Pharmacy and Chain of Pharmacies | In Progress | Present
13 | 2026-02-07 | Archana Jaharish | ISRO & Other official tasks | 1. Meeting with ISRO scientist for requirement gathering 2. Anupama's Laptop configuration and account setups 3. Testing the Add Patient and Sample Management functionality in Lab Module. | Completed | Present
14 | 2026-02-07 | Roshni | Training | Training UI - practice on login webpage | Submitted for review | Present
15 | 2026-02-07 | Nisarga | KT Session | Gathering KT for all the modules | In Progress | Present

## 03-Jul-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-07-03 | Shreeraksha | Pharma Module | Set the Cookie domain in backend code. Added email registration validation in backend Added validation according to SRS for user registration in frontend Added new toast component in frontend | Completed | Present
2 | 2026-07-03 | Prabhas K S | Pharma Module | developed New dashboard , developed logout flow, login and otp validation and rules , Side bar updated, implemented api interceptor | Completed | Present
3 | 2026-07-03 | Basavaraju N N | Pharma Module | Updated API for email otp verification flow with proper error message and validation | Completed | Present
|  |  |  | Working on user table creation for admin module, And Implimenting Api's for Admin login and logout. | In Progress
4 | 2026-07-03 | S J Yasshraj Vijayan | Lab Module | Lab Report - UI | Completed | Present
|  |  |  | AI Integration in Lab Report | In Progress
5 | 2026-03-07 | Rajani.I.R | Lab Module | 1.Retesting of fixed bugs and complete end to end testing of patient manageement and sample managment section | Completed | Present
|  |  |  | 2.Role based testing - Deskrole and Technician is carried out | Completed
|  |  | Pharma Module | 1. Testcases writing for registry and login page | Completed
6 | 2026-03-07 | Dipak | Lab Module | Implemented backend API integration for the Super Admin “Tests by Categories” pie chart dashboard, enabling dynamic retrieval and visualization of date-wise test data from the database. | Completed | Present
7 | 2026-03-07 | Ashik joshi | Inventory Module | "1.Reviewed the Software Requirements Specification (SRS) for the Inventory module. | In Progress | Present
8 | 2026-03-07 | Somil Merugawar | Pharma Aggaregater | Performed debugging and analysis of the Seller Module, including the signup, login, and Tiameds Admin compliance workflows. | In Progress | Present
9 | 2026-03-07 | Sunny | Lab module | All Bugs related with Sample management fixed | Completed | Present
10 | 2026-03-07 | Roshni Mohan | Training | Taken backup from prajwal account to my account | Completed | Present
11 | 2026-03-07 | Nisarga | Training | Gathering KT for all modules | In Progress | Present
12 | 2026-03-07 | Moses |  |  |  | Absent
13 | 2026-03-07 | Amit Hosmani | Pharma Module | Updated Application Status Tracking & Dashboard Access Use Case in the SRS | Completed | Present
14 | 2026-03-07 | Harshith | Training | Completed test cases | Completed | Present
15 | 2026-03-07 | Archana | ISRO & Other official tasks | Discussions followed by emails for account and laptops to the IT team Discussion with Nisarga for her training plan Gathered the hardware requirements and approximate costs for Uttarakosha and emailed to Captain and Abhinandan | Completed | Present

## 6-07-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 6/7/2026 | Rajani.I.R | Lab software Support | Support provided to Kaveri hospital for login and patient details age edit. New test was added for kaveri hospital on request | Completed | Week Off
| 2026-06-07 |  | Lab module | End to end testing done and testing observations are recorded. Also fixed bug is retested | Completed | Present
|  |  | Pharma Module | Test cases writing for dashboard page | In progress
|  |  | Lab software support | Reference range of TSH test altered for Talakadu hospital - request received from hospital. Changes were made only after cross verifying with Disha hospital test references | Completed
2 | 2026-06-07 | S J Yasshraj Vijayan | Lab module | Lab Report - AI Integration | In progress | Present
3 | 2026-06-07 | Shreeraksha | Pharma Module | Added JWT filter and Security config in backend | Completed
Worked on Pharmacy Details
4 | 2026-06-07 | Dipak | Lab module | Implemented backend API integration for the Super Admin Sample Status Overview , enabling dynamic retrieval and visualization of date-wise patient test summary data, including Total, Pending, Cancelled, Partially Completed, and Completed test counts from the database | Completed | Present
5 | 2026-06-07 | Ashik joshi | Inventory Module | 1.Reviewed the Software Requirements Specification (SRS) for the Inventory module. 2.Guided and trained a junior team member on SDLC and STLC fundamentals to enhance understanding of software development and testing processes. | In Progress | Present
6 | 6/7/2026 | Somil Merugawar | Uttara Kosha(ISRO) | Reviewed infrastructure requirement documents and performed analysis and discussions related to AI model requirements. | Completed | Present
|  |  | MarketPlace | Debug flow to implement manufacture user can add stock and update stock related feature. | In progress
7 | 6/7/2026 | Sunny | Lab module | Patient Managemnet - Bill printing & pdf generation bug fixed. | Completed | Present
8 | 2026-06-07 | Harshith | Training | learnt about software life cycle development | Completed | Present
9 | 2026-06-07 | Moses | Lab module | Add new test - test parameters config - numeric | Completed | Present
10 | 2026-06-07 | Basavaraju N N | Pharma Module | completed user table creation for admin module, And Implimented Api's for Admin login and logout. | Completed | Present
11 | 2026-06-07 | Prabhas K S | Pharma Module | 1)Developed the business details componenet, 2) api integration of admin module for auth related activities | 1) completed , 2) inprogress | Present
12 | 2026-06-07 | Nisarga GIri | Training | Created logiin page | Completed | Present
13 | 2026-06-07 | Roshni Mohan | Training | Updated login page | Completed | Present
14 | 2026-06-07 | Amit Hosmani | On Leave | On Leave | On Leave | Absent
15 | 2026-06-07 | Archana Jagadish | Training | Gave an overview of Software and different techniques and tools invloved in it to the new joinees | Completed | Present
|  |  | Pharma Inventory | SRS document review | In progress

## 7-07-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-07-07 | Harshith Gowda | Training | learnt about SRS,FRS,STLC,SDLC | Done | Present
2 | 2026-07-07 | Rajani.I.R | Pharma Module | 1.Testcases writing for dashboard page | Completed | Present
|  |  |  | 2.Testing of Create account page | Completed
|  |  |  | 3.Testing of login page | In progress
|  |  | Lab module support | Test references for Troponin I test was changed for Cureplus Martalli hospital on request. Disha hospital references are refered before changing | Completed
3 | 2026-07-07 | Prabhas K S | Pharma Module | 1)Fixed UI related changes wrt business details screens | Completed | Present
|  |  |  | 2) Integrated auth related api's in admin module (frontend) | Completed
4 | 2026-07-07 | S J Yasshraj Vijayan | Lab Module | Lab Report - AI Integration | In Progress | Present
5 | 2026-07-07 | Shreeraksha | Pharma Module | Worked on Pharmacy detials screen as per UI design | Completed | Present
6 | 2026-07-07 | Roshni Mohan | Training | Revised about software development cycle and javascript | Completed | Present
7 | 2026-07-07 | Nisarga Giri | Training | Updated login page, revised software development cycle & javascript | Completed | Present
8 | 2026-07-07 | Basavaraju N N | Pharma Module | Completed Admin Actions(Accept and Reject) | Completed | Present
9 | 2026-07-07 | Moses | Lab Module | creating pages for Add new test - test parameters config pages | Completed | Present
10 | 2026-07-07 | Sunny | Lab module | Lab Test Management - Implemented the new UI screen for the Test List & Updated the layout to align with the latest design requirements. | Completed | Present
|  |  |  | Lab Test Management - New Test Addition UI screen changes | In progress
11 | 2026-07-07 | Somil Merugawar | MarketPlace(Pharma Aggregator) | Seller users can add new stock batches and update existing stock batch details through the Stock Management feature. | In progress | Present
12 | 2026-07-07 | Dipak | Lab Module | Developed backend APIs for the Super Admin Top Referring Doctors dashboard to fetch and display date-wise referring doctor data dynamically from the database. | Completed | Present
13 | 2026-07-07 | Ashik joshi | Inventory Module | 1.Reviewed the Software Requirements Specification (SRS) for the Inventory module. 2.Guided and trained a junior team member on Development fundamentals to enhance understanding of software development and testing processes. | Completed | Present
14 | 2026-06-07 | Amit Hosmani | On Leave | On Leave | On Leave | Absent
15 | 2026-06-07 | Archana Jagadish | UI/UX of Pharma Inventory | Looking into the UI/UX of Pharma Inventory in Figma | In progress | Present
|  |  | Pharma Inventory | SRS document review | Completed
|  |  | Others | Other tasks | Completed

## 8-7-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-07-08 | Shreeraksha | Pharma Module | Implemented open API to fetch address details through pincode | Completed | Present
Added GST & PAN fields in Organization and Pharmacy Details
Created a Compliance Success Popup Modal in frontend
2 | 2026-07-08 | Harshith Gowda | Training | Learning about TiaMeds Marketplace platform (SRS) | In Progress | Present
3 | 2026-07-08 | S J Yasshraj Vijayan | Lab Module | Lab Report - AI Integration , UI Fixes | In Progress | Present
4 | 2026-07-08 | Moses | Lab Module | creating pages for Add new test - test parameters config pages - Multi-Parameter Creating mockup for marketplace | Completed | Present
5 | 2026-07-08 | Prabhas K S | Pharma Module | 1)API integration of pharma backend to frontend (organization details), 2) API integration of admin backend in frontend (business details) | 1)Completed, 2)InProgress | Present
6 | 2026-07-08 | Rajani.I.R | Pharma Module | Login page testing | Completed | Present
|  |  | Lab Module | 1.Meeting with SME's to gather feedback on lab enhancement - Feedback is noted and discussion with Archana, Amit done | Completed
|  |  |  | 2.Creating 39 patients data for testing of newly developed AI interpretation report | Data creation done report generation in progress
7 | 2026-07-08 | Dipak | Lab Module | Developed backend APIs for the Super Admin Health Snapshot dashboard to dynamically retrieve and display date-wise health parameter trends from the database. | Completed | Present
8 | 2026-08-07 | Basavaraju N N | Pharma Module | Included PAN, GST, and organization details fields in the Pharma Registration entity and updated the corresponding endpoints. | Completed | Present
|  |  |  | Currently working on the document URL update process after the admin approves a pharma request. | In Progress | Present
9 | 2026-08-07 | Nisarga Giri | Training | Created E commerce webpage, revised JavaScript | In Progress | Present
10 | 2026-08-07 | Roshni Mohan | Cureplus Blood bank website | Updated Phone number | Completed | Present
|  |  | Training | Revised Typescript | In Progress | Present
11 | 2026-08-07 | Ashik Joshi | Inventory Module | 1.Reviewed the Software Requirements Specification (SRS) for the Marketplace module. 2.Guided and trained a junior team member on Testing fundamentals to enhance understanding of software development and testing processes. | In Progress | Present
12 | 2026-08-07 | Archana Jagadish | Lab Module | Meeting with SME's about related bugs | Completed | Present
|  |  | Resume Screening | Shortlisted two engineers for mobile development | Completed
|  |  | Blood Buddy | Understanding the UI/UX | Completed
|  |  | Others |  | Completed
13 | 2026-08-07 | Chiranjeevi Santhosh | Training | I am start working with React JS | In Progress | Present
14 | 2026-08-07 | Sunny | Lab module | Lab Test Management - New Test Addition UI screen design | In progress | Present
|  |  |  | Lab Test Management - Implementation and validation of the New Test Addition UI screen | In progress
15 | 2026-08-07 | Somil Merugawar | Pharma Aggregator(Marketplace) | Batch wise stock management Feature implementation | Completed | Present
|  |  |  | Product variant and batch-wise stock management changes | In Progress
16 | 2026-08-07 | Amit Hosmani | Inventory Module | Assiting on PAN and GST capture for Business Setup and Entity Setup | Completed | Present
|  |  | Lab Module | Attended meeting with SMEs to understand the new enhancements and noted the bugs in enhanced UI/UX | Completed
|  |  | Beyond Bengaluru - BLUE Pitch | Drafting the beyond Bengaluru BLUE pitch deck | In Progress
17 | 2026-07-08 | Shreya M M | Internship | KT | In Progress | Present

## 9-7-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-07-09 | Shreeraksha | Pharma Module | Wrote a backend code to fetch organization details | Completd | Present
Added env variables in Vercel for both Pharma & Admin test env
Debugged CORS config issue
2 | 2026-07-09 | Basavaraju N N | Pharma Module | Worked on document URL update process after the admin approves a pharma request. | Completed | Present
Debugged CORS config issue
3 | 2026-07-09 | Prabhas K S | Pharma Module | 1)Integrated Organization details endpoint to pharma frontend, 2)Integrated Pharmacy details endpoint to admin Frontend, 3) Debugged CORS config issues | 1)Completed, 2)Completed, 3)Completed | Present
4 | 2026-09-07 | Rajani.I.R | Lab module | 1.Testing on lab report generation . Issues were recorded in the bug sheet | In progress | Present
|  |  |  | 2.Discussion with Amit,Moses,Sunnny and Yash was done on report UI/UX and Test master data | Completed
|  |  | Pharma Marketplace | 1.KT given to Roshni on Seller registration . Entire flow from seller registration,admin approvals and product onboarding was conveyed | Completed
5 | 2026-07-09 | Santhosh raju | TiaMeds Marketplace | I worked on PPT (Problem Statement) | In progress | Present
6 | 2026-07-09 | Harshith Gowda | Training | written test cases on TiaMeds marketpace platform(SRS) | In progress | Present
7 | 2026-07-09 | Nisarga Giri | Training | Editing the ppt document (socio-economic impact of the project) and practiced javascript | In progress | Present
8 | 2026-09-07 | Roshni Mohan | TiaMeds Marketplace | Recording video of workflow of website | Completed | Present
|  |  |  | Editing the video to minimum time | In progress | Present
9 | 2026-07-09 | S J Yasshraj Vijayan | Lab module | AI Integration in reports, UI bugs and fixes | Completed | Present
10 | 2026-07-09 | Ashik Joshi | Marketplace Module | 1.Reviewed the Software Requirements Specification (SRS) for the Marketplace module, discussed same with dev and BA team 2.Guided and trained a junior team member on Testing fundamentals to enhance understanding of software development and testing processes. | In Progress | Present
11 | 2026-09-07 | Dipak | Lab module | Implemented backend APIs for the Super Admin Lab Performance Summary Dashboard to dynamically retrieve and display date-wise lab performance metrics from the database. | Completed | Present
12 | 2026-09-07 | Moses | Pharma Module | dashboard status for multiple application status | Completed | Present
13 | 2026-09-07 | Archana Jagadish | On Leave | On Leave | On Leave | Absent
14 | 2026-09-07 | Sunny | Lab module | Lab Test Management - New Test Addition UI screen design | Completed | Present
15 | 2026-09-07 | Somil Merugawar | Pharma Aggregator( Marketplace) | Frontend and backend implment stock update batch ways and new batch create with variants | Completed | Present
16 | 2026-09-07 | Amit Hosmani | Lab module | UI Assistance for Test Master Creation & Report genration with AI | In progress | Present
|  |  | Beyond Bengaluru - BLUE Pitch | Updating the drafted beyond Bengaluru BLUE pitch deck - Problem Statement, Product/ Solution - Innovation | Completed
17 | 2026-09-09 | Shreya M M | Internship | KT | Completed | Present

## 10-7-26
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-10-07 | S J Yasshraj Vijayan | Lab Module | AI Integration , Package Management UI , Bug fixes | Completed | Present
|  |  |  | Report UI Alignment | In Progress
|  |  |  | SME Meeting , Fun Friday Activity L&D | Completed
2 | 2026-10-07 | Harshith Gowda | Training | Practiced test cases and SRS overview | Completed | Present
3 | 2026-10-07 | Rajani.I.R | Lab Module | 1.End to end testing of lab module - patient registry to report generation | Completed | Present
|  |  |  | 2.Meeting with SME's for module demo & feedbacks were noted | Completed
3.Fun Friday activity organised by L&D team was attended
|  |  | Pharma module | 4.Testing of login ,registry and compliance page | In Progress
4 | 2026-10-07 | Prabhas K S | Pharma | 1) Worked on validation, 2) Attended Demo give to SMES, 3)Attended Fun Friday activity Conducted by L&D Team | 1)InProgress, 2)Completed, 3)Completed | Present
5 | 2026-10-07 | Shreeraksha | Pharma Module | Added validation in Pharmacy Details | In progress | Present
|  |  |  | Attented the Demo given to SME's | Complete
Attented the Fun Friday activity coundected by L&D
6 | 2026-10-07 | Basavaraju N N | Pharma Module | Working on API integration using an API key to access the Inventory secure APIs from the Admin Service | In Progress | Present
|  |  |  | Attended Fun Friday activity Conducted by L&D Team | Completed
|  |  |  | Attented the Demo given to SME's | Completed
7 | 2026-10-07 | Nisarga | Training | preparing PPT slides | In Progress | Present
|  |  |  | Attended meeting with SME's for module demo | Completed
|  |  |  | Fun activity | Completed
8 | 2026-10-07 | Roshni Mohan | Training | Attended meeting with SME's for module demo | Completed | Present
Fun activity
Submitted corrected video
9 | 2026-10-07 | Sunny | Lab module | Super Admin Role - Reviewed the existing Dashboard design to understand the current implementation and functionality. | Completed | Present
Admin Role - Reviewed the existing Dashboard design to understand the current implementation and functionality.
Attended & delivered Demonstration of Lad Module during Sprint Progress Demonstration Meeting with SMEs.
10 | 2026-10-07 | Chiranjeevi Santhosh | Training | preparing PPT slides | In Progress | Present
|  |  |  | Attended meeting with SME's for module demo | Completed
|  |  |  | Fun activity | Completed
11 | 2026-10-07 | Somil Merugawar | MarketPlace Module | Attended & delivered Demonstration of MarketPlace Module during Sprint Progress Demonstration Meeting with SMEs. | Completed | Present
|  |  |  | Seller User can add product without variant and batch details Feature | In Progress
12 | 2026-10-07 | Ashik Joshi | Marketplace Module | 1.Reviewed the Software Requirements Specification (SRS) for the Marketplace module, discussed same with dev and BA team 2.Guided and trained a junior team member on Testing fundamentals to enhance understanding of software development and testing processes. | In Progress | Present
13 | 2026-10-07 | Amit Hosmani | MarketPlace Module | Assisting on the stock update sub module | Completed | Present
|  |  | Beyond Bengaluru - BLUE Pitch | Updating the drafted beyond Bengaluru BLUE pitch deck - Problem Statement, Product/ Solution - Innovation | Completed
|  |  | Sprint status update | Demonstration of sprint 2 status update - Lab, Pharma & Marketplace to SMEs and gathering inputs | Completed
|  |  | Inventory Module | Assisting on the super admin dashboard - application status overview | Completed
|  |  | Lab Module | Assisting on the test report generation | In Progress
14 | 2026-10-07 | Dipak | On Leave
15 | 2026-10-07 | Moses | Pharma module | Updating Business Dashboard - Super Admin | In Progress | Present
|  |  | Lab Module | Updating Super Admin Dashboard | In Progress
16 | 2026-10-07 | Archana | ISRO | Attended Requirment Gatherin meeting for Uttara Kosha with ISRO scientist | Completed | Present
|  |  | Other Activities | Claude license estimation | In Progress
17 | 2026-07-10 | Shreya M M | Training | Developing AI Chatbot | Completed | Present

## 13-7-26
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 13/07/2026 | S J Yasshraj Vijayan | Lab Module | Lab Report - UI Alignments | Completed | Present
2 | 2026-11-07 | Rajani.I.R | Support for Lab module | 1.Cureplus hospital Talakadu - References were changed on hospital request . Two parameters were added in Urine routine test | Completed | Week off
2.Disha Hospital - 1 New test NT pro BNP was added
| 13/7/26 |  | Lab Module | 1.End to end testing . 18 reports were generated by adding original test data from Cureplus hospitals. Reports sent to Sini mam for review | Completed | Present
|  |  | Pharma Module | 1.Writing testcases for business set up page | In progress
3 | 13/7/2026 | Harshith Gowda G | Training | written test cases on marketplace flatform (SRS) | Completed | Present
4 | 13/7/26 | Shreya M M | Training | Concepts of Node JS and react frontend - handwriting recognition | completed | Present
5 | 13/7/26 | Prabhas K S | Pharma Module | Added validation and added error handeling for business setup form | Completed | Present
6 | 13/7/26 | Basavaraju N N | Pharma Module | Worked on API integration using an API key to access the Inventory secure APIs from the Admin Service | Completed | Present
7 | 13/7/26 | Chiranjeevi Santhosh | Training | I worked on a basic project built with Spring Boot and React (TypeScript). | Completed | Present
8 | 13/7/27 | Nisarga Giri | Training | Prepared a ppt slide and Making modifications in Cureplus website | In progress | Present
9 | 13/07/26 | Roshni Mohan | Cureplus website | Making modifications as per requirement | In progress | Present
10 | 2026-11-07 | Amit Hosmani | Beyond Bengaluru - BLUE Pitch | Drafted & completed beyond Bengaluru BLUE pitch deck | Completed | Week off
| 13/07/26 |  | Beyond Bengaluru - BLUE Pitch | Demonstrating the drafted beyond Bengaluru BLUE pitch deck to SVP and VP of TiaMeds | Completed | Present
|  |  | Pharma Module | R&D for Super Admin adding roles and responsibilities for Admin and Desk role. | In progress
|  |  |  | R&D for onboarding suppliers | In progress
|  |  |  | R&D for raising Purchase Order | In progress
|  |  | Other Activities - Interview | Conducted 2nd round of interview for mobile app developer | Completed
11 | 13/07/26 | Sunny | Lab module | Super Admin Dashboard:- Started developing the dashboard implementation on frontend and preparing the components for API integration | In progress | Present
12 | 13/07/26 | Dipak | Lab module | Implemented backend APIs for the Super Admin Top Revenue by Lab Dashboard to dynamically fetch and display date-wise lab performance metrics from the database. | Completed | Present
13 | 13/07/26 | Ashik Joshi | Marketplace Module | 1.Reviewed the Software Requirements Specification (SRS) for the Marketplace module, discussed same with dev and BA team 2.Guided and trained a junior team member on Testing fundamentals to enhance understanding of software development and testing processes. | In Progress | Present
14 | 13/07/26 | Somil Merugawar | Marketplace Module | Batch-wise stock update changes and new batch creation flow for product variants | In progress | Present
|  |  | Uttara kosha | Offline different Model test to generate as our requirement output and image | In progress
|  |  | Other | Bug resolve with Sunny lab Management Project | Completed
15 | 13/07/26 | Moses | Lab Module | Updating Super Admin Dashboard | Completed | Present
16 | 13/07/2026 | Archana Jagadish | Uttara Kosha | Trying and testing different LLMs | In Progress | Present
|  |  | Recruitment | Interview for Mobile App Developer | Completed
|  |  | Lab Module | Comparison with Ayus, DocPulse and Softclinics | Completed
|  |  | Others |  | Completed

## 14-Jul-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-07-14 | Shreeraksha | Pharma Module | Worked on the dashboard screen which shows Application Status in frontend | In Progress | Present
|  |  |  | Changed the scheduling of Pharma Test Service in AWS | Completed
2 | 2026-07-14 | shreya M M | Training | Developed an AI handwriting recognition system, updated the frontend and integrated the backend for text conversion | In Progress | Present
3 | 2026-07-14 | Prabhas K S | Pharma Module | 1)Updated confirm pop modal to have add location option(button) that redirects to render new form to create new entities for multi location organizations,, 2)Api endpoint to retrive all the pharmacies per user id in admin backend | 1)Completed , 2)Inprogress | Present
4 | 2026-07-14 | Basavaraju N N | Pharma Module | Worked on API creation part for User Dashboard KPIs like Total pharmacies, Approved, Under Review, Action Required and Rejected. | Completed | Present
5 | 2026-07-14 | S J Yasshraj Vijayan | Lab Module | Working on the lab module UI screens, big fixes and enhancements | In Progress | Present
| 2026-07-14 | Chiranjeevi Santhosh | Training | I am working on the login page and implementing JWT token timeout. | In Progress | Present
7 | 2026-07-14 | Nisarga Giri | Training | Modifying the CurePlus website | In Progress | Present
8 | 2026-07-14 | Roshni Mohan | Training | Working on modificatin of cureplus disha hospital webpage | In Progress | Present
9 | 2026-07-14 | Harshith Gowda | Training | Reviewed the Software Requirements Specification (SRS) for the Marketplace module | In Progress | Present
10 | 2026-07-14 | Amit Hosmani | Pharma Module | Updating SRS and assisting for UI/UX on Super Admin performing User Management - Add, Delete, Edit | In Progress | Present
|  |  | Lab Module | Assisting for Super Admin dashboard with updated KPIs, Charts and Filters to developers | In Progress
11 | 2026-07-14 | Sunny | Lab module | Super Admin Dashboard:- Developement of Frontend UI design as per figma | Completed | Present
|  |  |  | Super Admin Dashboard:- Integration of API with new UI Dashboard | In Progress
12 | 2026-07-14 | Somil Merugawar | MarketPlace | Implemented the Add Product Details only workflow with support for multiple product categories | Completed | Present
|  |  |  | Modified the Batch-wise Stock Update workflow | Completed
|  |  |  | Implemented the New Batch Creation workflow with product variant support | Completed
|  |  | Uttara Kosha | Conducting R&D on local AI models for PDF upload, document accuracy evaluation, and infrastructure assessment | In Progress
13 | 2026-07-14 | Dipak | Lab Module | Implemented backend APIs for the Super Admin dashboard to dynamically retrieve and visualize category-wise test counts and revenue with date-wise filtering from the database. | Completed | Present
14 | 2026-07-14 | Ashik Joshi | Inventory Module | 1.Attended the Vignyan Labs meeting for the Uttarakosha project. 2.Tested the Inventory module and raised issues. 3.Guided and trained a junior team member on writing test cases. | In Progress | Present
15 | 2026-07-14 | Rajani | On Leave | On Leave | On Leave | Absent
16 | 2026-07-14 | Archana Jagadish | Uttarakosha | Meeting with Vigyan Labs, Testing a few LLMs | In Progress | Present
|  |  | Lab Module | Review of the Super Admin Dashboard | Completed
|  |  | Others |  | Completed

## 15-7-26
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 15/7/26 | Rajani.I.R | Lab module support | Kaveri Hospital - Double marker test added, NMH - Price was added for ferritin test [price approved from Manjunath Sir], Dharani Hospital - Test values were edited as they had entered wrong report | Completed | Present
|  |  | Lab Module | Testing of report allignments and AI interpretations | Completed
|  |  | Pharma Marketplace | Testing of batch update feature | In progress
2 | 15/7/26 | Shreeraksha | Pharma Module | Worked on the dashboard screen which shows Application Status in frontend | Complete | Present
3 | 15/7/26 | Prabhas K S | Pharma and Admin | 1)Created API for retrieveing all the Pharmacy per user in admin backend,, 2) Api integration for Pharmacy display in Pharma frontend dashboard | 1)Completed, 2)Inprogress | Present
4 | 15/7/2026 | Basavaraju N N | Pharma Module | Worked on Update Pharmacy endponit. | Complete | Present
5 | 15/7/2026 | Chiranjeevi Santhosh | Training | I am working on the implementing JWT token timeout. | Complete | Present
6 | 15/7/2026 | Shreya M M | Training | Implemented frontend enhancements for the Handwriting Recognition System | Completed | Present
7 | 15/7/2026 | Nisarga Giri | Training | Working on R&D for marketplace entities | In progress | Present
8 | 15/07/2026 | Roshni Mohan | Training | Working on Cureplus Disha Hospital website | In progress | Present
9 | 15/07/2026 | Dipak | Lab Module | Developed backend APIs for the Super Admin Package-wise Revenue Dashboard to dynamically fetch and display date-wise revenue data from the database. | Completed | Present
10 | 15/07/2026 | Somil Merugawar | MarketPlace | Add the missing Packaging fields in the Update Stock page: Shelf Life (Months), Special Offer Discount (%), GST, and HSN Code. | In progress | Present
|  |  |  | Stock Management: Added the option to delete product batches, including their associated batch details. | In Progress
11 | 15/07/2026 | Sunny | Lab Module | Super Admin Dashboard:- Integration of API with new UI Dashboard | In progress | Present
|  |  |  | Attended & delivered Demonstration of Lad Module during Sprint Progress Demonstration Meeting with Arjun Sir | Completed
12 | 15/07/2026 | moses | Pharma Module | Creating User Management Complete Flow | Completed | Present
13 | 15/07/2026 | Ashik Joshi | Inventory Module,Marketplace | 1.Reviewed the UI screens for the Inventory User Management module. 2.Wrote test cases for the Marketplace Landing Page. 3.Attended the project demo. | In progress | Present
14 | 15/07/2026 | Amit Hosmani | Pharma Module | Assisting User Management UI/UX design - Add user, assign role, manage user | Completed | Present
|  |  |  | Updating SRS for User Managemet - Add User, Role Mapping | In Progress
|  |  | MarketPlace | Assisting Add stock functionality with batch management, price management and Discuount management | Completed
|  |  | Lab Module | Assisting on updated KPIs and Charts to be showcased in Super Admin dashboard - Revenue by packages, Total Billed Amount, Amount collected, Amount pending | Completed
15 | 15/07/2026 | Yash | On Leave | On Leave | On Leave | Absent
16 | 15/07/2026 | Archana Jagadish | Lab Module | Dashboard review | In Progress | Present
|  |  | Cureplus website requirements review | Reviewed the requirements of Cureplus website requirements | Completed
|  |  | Uttarakosha | Research and Development | In Progress
|  |  | others |  | Completed

## 16-7-26
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 16/07/26 | S J Yasshraj Vijayan | Lab Module | Store AI observations of lab report - Backend - discussed regarding the worklfow with Dipak sir. | Completed | Present
|  |  |  | Frontend screen assigned - Doctor Management | In Progress
2 | 16/07/2026 | Nisarga Giri | Training | Worked on R&D for marketplace remaining entities | Completed | Present
3 | 16/7/26 | Rajani.I.R | Pharma Inventory | 1.Test cases writing for business registration | Completed | Present
|  |  |  | 2.Testing of Business registration page and bugs reported in bug sheet and conveyed to developers | Completed
4 | 16/7/26 | Roshni Mohan | Training | Worked on FAQ section in Cureplus Disha Hospital Website | Completed | Present
5 | 16/7/26 | Prabhas K S | Pharma Inventory | 1)Dashboard Kpi api Integration 2) view Pharma details Modal 3)User management add User Wizard Screen (Personal details capture), 4)User Management Add user Wizard (Role management) | 1)Comlpeted 2)Completed 3) Completed 4)Completed | Present
6 | 16/07/26 | Santhosh Raju | Pharma Aggregator | I am working on the Pharma aggregator project, code review and project structer | In Progress | Present
7 | 16/07/2026 | Shreya M M | Training | working on report analyzer project | In Progress | Present
8 | 16/07/2026 | Shreeraksha | Pharma Module | Worked on User List screen | Completed | Present
9 | 16/07/2026 | Basavaraju N N | Pharma Module | Added new fields in User Entity table and Created FindAllUsers and FindUserById Endpoints. | Completed | Present
|  |  |  | Working on User-Management flow module, feature and permission mapping, etc | In Progress
10 | 16/07/2026 | Somil Merugawar | MarketPlace | Edit Product page five Categories component by removing unused code and updating validation schema | Completed | Present
|  |  |  | Stock Management Table in Delete Batch field | In Progress
|  |  |  | Add New Batch in add Self life field , add special discount percentage field | In Progress
11 | 16/07/2026 | Dipak | Lab Module | Developed backend APIs for the Super Admin Category wise tests Dashboard to dynamically fetch and display date-wise revenue data from the database. | Completed | Present
12 | 16/07/2026 | moses | Lab Module | Doctor Management pages | Completed | Present
13 | 16/07/2026 | Sunny | Lab module | Super Admin Dashboard:- Developed the dashboard UI and integrated APIs to dynamically fetch and display category-wise & date-wise revenue data. | Completed | Present
14 | 16/07/2026 | Ashik Joshi | Inventory Module,Marketplace | 1.Tested the Marketplace Landing Page and Registration Page. 2.Raised issues for the identified defects. 3.Discussed the requirements of the Inventory Module. | In progress | Present
15 | 16/07/2026 | Amit Hosmani | Inventory Module | Research on Product Master Management Module | Completed | Present
|  |  |  | Assisting UI/UX for Product Master Management Module | In Progress
|  |  |  | Research on Billing Module | In Progress
|  |  | Lab Module | Coordinating with team to update the Super Admin dashboard as the business requires | Completed
|  |  | MarketPlace | Coordinating with team to onboard the other entities - White Labelling Company, Distributor, PCD entities with their relevant compliance details | In Progress
16 | 16/07/2026 | Archana Jagadish | Lab Module | Discussion on SuperAdmin Dashboard | In Progress | Present
|  |  | MarketPlace | Assigned work to Santhosh on Onboarding Buyer | In Progress
|  |  | Others |  | Completed

## 17-7-26
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 17/07/26 | S J Yasshraj Vijayan | Lab Module | Doctor Management, Add Patient - Add Doctor frontend screens | Completed | Present
2 | 17/07/26 | Basavaraju N N | Pharma Module | Worked on User-Management flow module, feature and permission mapping, etc | Completed | Present
Worked on APIs to get required master APIs for user registration
3 | 17/7/26 | Rajani.I.R | Pharma Inventory | 1.Writing test cases for Dashboard page | Completed | Present
|  |  |  | 2.Testing of dashboard page | Completed
4 | 17/7/26 | Shreeraksha | Pharma Module | Created API to upload User image | Completed
|  |  |  | Created API to upload change the user status(Active, InActive) |  | Present
5 | 17/7/26 | Amit Hosmani | Pharma Module | Research on product onboarding with supplier information capture and documentation | Completed | Present
|  |  | Blue Bengaluru Pitch | Preparing for presentation pitch for today's presentation | Completed
6 | 17/07/26 | Sunny | Lab module | Super Admin Dashboard:- Deployed Super Admin Dashboard to the testing environment. | Completed | Present
|  |  |  | Admin Dashoboard:- Collaborated with Amit Sir and Dipak to finalize the data requirements and metrics to be displayed. | In progress
7 | 17/07/26 | Ashik Joshi | Marketplace |  | In progress | Present
8 | 17/07/26 | Nisarga Giri | Training |  | Completed | Present
9 | 17/07/26 | Somil Merugawar | Marketplace | 1.Tested the Marketplace Seller Registration Page. 2.Raised issues for the identified defects. 3.Discussed the requirements of the MarketPlace Module. | Completed | Present
|  |  |  | Worked on R&D for marketplace Registration page for other 3 entities | In progress
|  |  |  | Stock Management Table in Delete Batch field | In progress
10 | 17/07/2026 | Shreya M M | Training | implemented frontend features(Sorting,Filtering, Searching) for report analyzer project | In progress | Present
11 | 17/07/27 | Dipak | Lab Module | New Batch add time missing field self life and add special offers discount percentage field | Completed | Present
12 | 17/07/26 | Roshni Mohan | ARC Website | Implemented frontend features(Sorting,Filtering, Searching) for report analyzer project | In progress | Present
13 | 17/07/26 | Santhoshraju | Pharma aggregator | Developed backend APIs for the Admin Category wise tests Dashboard to dynamically fetch and display date-wise revenue data from the database. | In Progress | Present
Gathering requirements for website modification
I am working on the Pharma aggregator project, code review and project structer
14 | 17/07/2026 | Prabhas K S | Pharma Inventory | 1)Api integration of user management(add user) 3)Api integration Role permission 4) APi integration image upload 5) APi integration module and featuer masters 6)dropdown common componenet | Completed | Present
15 | 17/07/2026 | Moses | On Leave | On Leave | On Leave | Absent
16 | 17/07/2026 | Archana Jagadish | Uttarakosha | Tested the OCR trail url shared by vigyan labs | completed | Present
|  |  | Others | Git Hub, Pharma Inventory - Feature gathering | completed
|  |  | Beyond Bangalore BLUE | Pitch preparation | completed

## 20-7-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-07-20 | Rajani.I.R | Lab Module | 1Testing of superadmin page and recording testing observations | In Progress | Present
|  |  |  | 2.Meeting with Sini Mam - received feedback for lab reports | Completed
|  |  | Pharma Module | 1.Writing test cases for user management | In Progress
2 | 2026-07-20 | S J Yasshraj Vijayan | Lab Module | Meeting with Sini ma'am | Completed | Present
|  |  |  | Report UI - Changes | In Progress
3 | 2026-07-20 | Shreeraksha | Pharma Module | API integration of Pharma Module | Completed | Present
4 | 2026-07-20 | Harshith Gowda | Training | Reviewed the TiaMeds marketplace and written defeacts of landing page | Completed | Present
5 | 2026-07-20 | Santhosh Raju | Pharma aggregator | I worked on Spring Boot CRUD operations with React and TypeScript. | Completed | Present
6 | 2026-07-20 | Prabhas K S | Pharma Module | 1)Api integration for role Management create(debug) 2)Api integration Role management view /user 3)Validation for image upload 4)Pushed all changes to test | Completed | Present
7 | 2026-07-20 | Nisarga Giri | Training | Reviewed and updated mandatory and optional fields for White Labeling, Distributor, and PCD. | Completed | Present
8 | 2026-07-20 | Shreya M M | Training | Implemented dashboard , API-based Excel integration, and tested SharePoint live data access. | In Progress | Present
9 | 2026-07-20 | Roshni Mohan | Training | Mandatory Required data columns added in excel sheet | Completed | Present
10 | 2026-07-20 | Sunny | Lab module | 1. Admin Dashboard:- Developement of Frontend UI design as per figma | Completed | Present
|  |  |  | 2. Admin Dashboard:- Integration of API with new UI Dashboard | In progress
|  |  |  | 3. Landing Page: New Landing Page UI | In progress
11 | 2026-07-20 | Ashik Joshi | Inventory Module,Lab Module | 1.Tested the Lab module DashBoard. | In progress | Present
2.Raised issues for the identified defects and Discussed with Dev and BA.
3.Discussed the requirements of the Inventory Module.
12 | 2026-07-20 | Somil Merugawar | MarketPlace | Added missing fields and Special Discount fields to the New Batch creation process. | Completed | Present
|  |  |  | Added Seller Onboarding support for PCD, Distributor, and Whitelist Company user types. | In Progress
13 | 2026-07-20 | Dipak | Lab Module | Developed backend APIs for the Admin Dashboard to dynamically retrieve and display lab-wise KPIs, including Total Revenue, Total Tests, Total Patients, Pending Samples, and Reports Generated, with date-wise data fetched from the database. | Completed | Present
14 | 2026-07-20 | Amit Hosmani | Pharma Module | Updation on Purchase Entry - Product Catalogue, Add New Product (Drugs), Add Packaging Details, Add Pricing Details | Completed | Present
|  |  |  | Update Stock for existing product - Drugs | In Progress
|  |  | MarketPlace | Data fileds finalization to onboard the White Label Company, Distributor and PCD entities | Completed
15 | 2026-07-20 | moses | Pharma Module | Purchase Management -> add new -> drug category pages | Completed | Present
16 | 2026-07-20 | Basavaraju | on leave | on leave | on leave | Absent
17 | 2026-07-20 | Archana | on leave | on leave | on leave | Absent

## 21-7-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-07-21 | Rajani.I.R | Lab Module Support | 1.Support to Shanivarsanthe hospital - 2 tests[Hepatitis A Igm serum and Hepatitis A virus Igg antibody] in serology added [ price of the test approved by Manjunath sir] | completed | Present
2.Support to Kaveri hospital - resolved issue in registering a patient
3.Disha hospital - Few references were removed in FSH and LH test [unnecessary parameters]
|  |  | Lab Module | Testing of Report Generation and issues reported in bug sheet | In Progress
|  |  | Pharma Module | Test cases writing for User management | completed
2 | 2026-07-21 | Harshith Gowda | Training | 1,manual testing course | completed | Present
|  |  |  | 2,learnt SRS marketplace platform | completed
3 | 2026-07-21 | S J Yasshraj Vijayan | Lab Module | Frontend Screens and Lab Report changes | In Progress | Present
4 | 2026-07-21 | Prabhas K S | Pharma Module | Detailed discussion, database design and task discussion on - Product, Purchase & Supplier | Completed | Present
5 | 2026-07-21 | Basavaraju N N | Pharma Module | Detailed discussion, database design and task discussion on - Product, Purchase & Supplier | Completed | Present
6 | 2026-07-21 | Shreeraksha | Pharma Module | Detailed discussion, database design, ER Diagram preparation and task discussion on - Product, Purchase & Supplier | Completed | Present
7 | 2026-07-21 | Nisarga Giri | Training | Reviewed the marketplace workflow to understand the onboarding process for the remaining three entities. | Completed | Present
8 | 2026-07-21 | Roshni Mohan | Training | Finalized Product master creation document | Completed | Present
9 | 2026-07-21 | Shreya M M | Training | Worked on SharePoint Excel integration and identified access permission issues | In Progress | Present
10 | 2026-07-21 | Ashik Joshi | Lab Module | 1.Tested the Lab module Dashboard. | In progress | Present
2.Raised issues for the identified defects and Discussed with Dev and BA.
3.Guided and trained a junior team member on writing test cases.
11 | 2026-07-21 | Dipak | Lab Module | Implemented backend APIs for the Admin Lab Performance Summary Dashboard to dynamically retrieve and display date-wise sample workflow metrics, including samples registered, collected, results entered, reports generated, and reports delivered, with data fetched from the database. | Completed | Present
12 | 2026-07-21 | Somil Merugawar | Marketplace | Seller User Onboarding (White Label, Distributor, and PCD Entity) | In Progress | Present
13 | 2026-07-21 | Sunny | Lab module | 1. Sample Management :- Detailed Report Bug Fixing | Completed | Present
|  |  |  | 2. Admin Dashboard:- Developed the dashboard UI and integrated APIs to dynamically fetch and display category-wise & date-wise revenue data & Deployed same to testing environment | Completed
|  |  |  | 3. Landing Page: New Landing Page UI | In progress
14 | 2026-07-21 | Moses | Pharma Module | Purchase Management -> add new -> Supplements / Nutraceuticals category pages | Completed | Present
15 | 2026-07-21 | Amit Hosmani | Pharma Module | Update Stock for existing product - Supplements/ Nutraceuticals, Food & Infant Nutrition, Cosmetics & Personal Care, Consumable Medical Devices and Non consumable medical devices | completed | Present
|  |  |  | Discussion on product onboarding with variants and finalization of data fields to onboard the products | completed
|  |  | Marketplace | Data fields finalization for White labelling company, distributor, PCD to onboard them | completed
16 | 2026-07-21 | Gowtham | KT Session | KT Session on all the modules of TiaMeds | In Progress | Present
17 | 2026-07-21 | Archana | on leave | on leave | on leave | Absent

## 22-7-26
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-07-22 | Shreeraksha | Pharma Module | Worked on supplier master backend | Complete | Present
|  |  |  | Worked on Product Management backend | In progress
2 | 2026-07-22 | Rajani.I.R | Pharma module | Testing of complete user management | Completed | Present
3 | 2026-07-22 | Nisarga Giri | Training | Went through frontend, backend, and database integration for onboarding workflow | Completed
|  |  |  | Tested onboarding page and identified missing District/Taluk data issue due to empty database tables and Added district records in the database and verified data flow. | In progress | Present
4 | 2026-07-22 | Shreya M M | Training | updated the excel link to report analyzer project | In progress | Present
5 | 2026-07-22 | Basavaraju N N | Pharma module | Created required master tables for product(drug & supplements) onboarding and inserted masters data. | Completed | Present
|  |  |  | Working on supplier payment flow backend | In progress
6 | 2026-07-22 | Prabhas K S | Pharma Module | 1)Created Entities Product Maanagement 2) Created Repository Product 3) Created DTO for Product Onboarding (Suppliment) 4) Creating Service and controller (suppliment) | 1)Completed 2) Completed 3)Inprogress 4)Inprogress | Present
7 | 2026-07-22 | Roshni Mohan | ARC website | Worked on Features List document | Completed | Present
8 | 2026-07-22 | S J Yasshraj Vijayan | Lab Module | Frontend screens and lab report | In Progess | Present
9 | 2026-07-22 | Santhoshraju | Pharma aggregator | Worked on the "Become a Seller" registration page and implemented dropdowns, but the frontend API is not working. | In progress | Present
10 | 2026-07-22 | Amit Hosmani | Pharma Module | Finalizing data fields for Tax Invoice generation and assisting for figma design | In progress | Present
11 | 2026-07-22 | Somil Merugawar | MarketPlace | Marketplace seller onboarding for other entities (White Label, Distributor, and PCD) | In Progress | Present
12 | 2026-07-22 | Moses | Pharma Module | working on Purchase Invoice | In Progess | Present
13 | 2026-07-22 | Ashik Joshi | Lab Module,Inventory Module | 1.Tested the Lab module Admin Dashboard and AI interpretation . | In progress | Present
2.Raised issues for the identified defects and Discussed with Dev and BA.
3.Guided and trained a junior team member on writing test cases.
4.Tested Inventory module Business set up pages
14 | 2026-07-22 | Sunny | Lab module | 1. Landing Page: New Landing Page UI | Completed | Present
|  |  |  | 2. Navigation:- Updated the Patient Management and Sample Management navigation from a tab-based layout to a sidebar navigation. | Completed
15 | 2026-07-22 | Dipak | Lab Module | Implemented backend API integration for the Super Admin dashboard’s Tests by Categories and Gender-wise Tests charts, enabling dynamic retrieval and visualization of category-wise and gender-wise patient test data from the database. | Completed | Present
16 | 2026-07-22 | Archana Jagadish | Uttarakosha | Discussion on the effort estimate for proposal preparation | Completed | Present
|  |  | Others | Following up with Dr Sini on the Universal UI design, hardware requirement request for Mobile developer | Completed

## 23-7-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-07-23 | Rajani.I.R | Lab module | 1.Testing of Doctor management page | Completed | Present
|  |  |  | 2.Testing of Admin dashboard page | In progress
|  |  |  | 3.End to end testing of lab module | In progress
2 | 2026-07-23 | Harshith Gowda | Training | 1,reviewed marketplace and tested landing page and dashboard listed defects | Completed | Present
|  |  |  | 2,manual testing course | Completed
3 | 2026-07-23 | Nisarga Giri | Training | Tested seller onboarding for remaining entities and verified data in the local database | In progress | Present
4 | 2026-07-23 | Roshni Mohan | ARC website | Updated features List | In progress | Present
5 | 2026-07-23 | Basavaraju N N | Pharma Module | Worked on supplier payment flow backend | Completed | Present
Worked on Batch Details UI component for product onboarding
6 | 2026-07-23 | Prabhas K S | Pharma Module | 1)Service updated for Product Onboarding 2)Controller For Product Onboarding 3) APi testing for drug and supplimnt onboarding 4)Add Product Screen developed 5)Dynamic product details component developed 6)packaging details component developed | 1,2,4,5,6)Completed 3)Inprogress | Present
7 | 2026-07-23 | Shreya M M | Training | Updated Excel integration and verified all previous reports display correctly | Completed | Present
8 | 2026-07-23 | Santhoshraju | Pharma Aggregator | Worked on the "Become a Seller" registration page and implemented dropdowns, but the frontend API is not working. | Completed | Present
9 | 2026-07-23 | Shreeraksha | Pharma Module | Worked on Product Management backend | Completed | Present
Worked on Goods Receipt frontend screen
10 | 2026-07-23 | Dipak | Lab module | Developed backend APIs for the Super Admin Revenue by Lab and Revenue by Package dashboards, enabling dynamic retrieval and visualization of date-wise revenue data from the database. | Completed | Present
11 | 2026-07-23 | Ashik Joshi | Inventory Module,MarketPlace | 1.Tested Inventory module Business set up pages and User management and tested Market Place module | In progress | Present
2.Raised issues for the identified defects and Discussed issue with Dev Team
3.Guided and trained a junior team member on Testing.
12 | 2026-07-23 | Sunny | Lab module | 1. Sample Management :- Updated the UI for configuring new samples and enhanced the interfaces for editing and deleting existing samples. | Completed | Present
|  |  |  | 2. Super Admin Dashboard – Modified the frontend to accommodate changes in the backend APIs and ensured seamless integration with the updated API responses. | Completed
|  |  |  | 3. Bug Fixes – Fixed bugs in the Super Admin Dashboard to improve functionality and stability. | Completed
13 | 2026-07-23 | Somil Merugawar | MarketPlace | Market Place Onboarding Seller entity (Whitelable, Distributor and PCD) | Completed | Present
|  |  |  | Admin Approved Seller Registration and product categories | Completed
14 | 2026-07-23 | Moses | Pharma Module | working on Purchase Invoice | In Progress | Present
15 | 2026-07-23 | Amit Kumar Hosmani | Mysuru Big Tech Show 2026 |  | Completed | Present
16 | 2026-07-23 | Archana Jagadish | Mysuru Big Tech Show 2027 |  | Completed | Present

## 24-7-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-07-24 | Rajani.I.R | Lab Module | 1.Retested fixed bugs and reported the testing observation | Completed | Present
|  |  |  | 2.Super admin & admin dashboard testing | Completed
|  |  | Pharma Marketplace | 1.Seller registration as White labelling company | In progress
2 | 2026-07-24 | Nisarga Giri | Training | Tested the registration flow for the remaining 3 seller entities. | Completed | Present
Verified and approved registrations locally using Postman for all seller entities.
3 | 2026-07-24 | Santhosh Raju | Pharma Aggregator | Worked on the "Become a Seller" registration page. Filled all the required fields and uploaded the documents. On clicking Submit, I received a 400 Bad Request error. Debugged the issue and found that the required data is missing from the database. | Completed | Present
4 | 2026-07-24 | Shreya M M | Training | Tested and validated the Daily Report Dashboard using historical Excel data | Completed | Present
5 | 2026-07-24 | Roshni Mohan | ARC Website | Had a discussion regarding requirements with rajesh sir | Completed | Present
6 | 2026-07-24 | Shreeraksha | Pharma Module | Worked on the frontend of Purchase Module | In progress | Present
7 | 2026-07-24 | Basavaraju N N | Pharma Module | Worked on draft(backend part) for pharma business setup(raised on bug sheet) | Completed | Present
8 | 2026-07-24 | S J Yasshraj Vijayan | Lab Module | Lab AI Reports, UI and bug fixes | Completed | Present
9 | 2026-07-24 | Prabhas K S | Pharma Module | 1)Masters api integration for products 2) defect (14 - 23) resolved locally yet to push to test 3) fixed few other bugs related to business setup ,locally | completed | Present
10 | 2026-07-24 | Dipak | Lab Module | Worked on developing the Grid Report API endpoint to retrieve and deliver detailed report data from the database. | Completed | Present
11 | 2026-07-24 | Ashik Joshi | MarketPlace | 1.Tested Market Place - Register and Add product | In progress | Present
2.Raised issues for the identified defects and Discussed issue with Dev Team and BA
3.Guided and trained a junior team member on Testing.
12 | 2026-07-24 | Sunny | Lab module | 1. Sidebar :- Updated the sidebar navigation to match the latest Figma design | Completed | Present
|  |  |  | 2. Super Admin Dashboard – Modified the frontend to accommodate changes in the backend APIs. | Completed
13 | 2026-07-24 | Amit Hosmani | MarketPlace | Redefining login method for all the seller type to have the same login methodology across all the modules | Completed | Present
|  |  | Pharma Module | Internal discussion on the bugs raised on the Inventory module development | Completed
|  |  | L&D Session | Attended team collaboration session conducted by L&D team | Completed
14 | 2026-07-24 | Somil Merugawar | MarketPlace | Seller Registration: Validation Updates and Product Category Flow Changes | In progress | Present
|  |  |  | Add New Seller Login Seperate For current MarketPlace | In progress
15 | 2026-07-24 | Moses | Lab Module/ pharma | Changing the sidebar and creating screens for Medical devices & Equipments (Consumable and Non - Consumable Medical Devices & Equipments), Food & Infant Nutrition, Cosmetics & Personal Care | Completed | Present
16 | 2026-07-24 | Archana Jagadish | Others | Discussions, 1-1 | In Progress | Present

## 27-7-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-07-25 | S J Yasshraj Vijayan | Lab Module | Health Snapshot fixes. | Completed | Present
| 2026-07-27 |  |  | UI Screens of Patient Dashboard, Doctor | Completed | Present
|  |  |  | Bug fixes | Completed
2 | 27/07/2026 | Harshith Gowda | Training | tested on inventary screens | Completed | Present
|  |  |  | manual testing course | In progress | Present
3 | 27/07/2026 | Nisarga Giri | Training | Worked on bug fixing | In Progress | Present
4 | 2026-07-27 | Rajani.I.R | Lab module | Testing of fixed bugs in lab report section | Completed | Present
|  |  | Pharma Marketplace | Seller registration as White labelling company - testing | Completed
|  |  | Lab module support | Support provided to Talakadu hospital - Xray price change and help in printing of report | Completed
5 | 2026-07-27 | Shreya M M | Training | Started building the inventory expiry & stock alert system | Completed | Present
6 | 2026-07-27 | Roshni Mohan | Pharma Module | 4 bugs are fixed | In Progress | Present
7 | 2026-07-27 | Basavaraju N N | Pharma Module | Worked on draft(frontend part) for pharma business setup(raised on bug sheet) | Completed | Present
Created Master Tables, Inserted Master Data's, Created Endpoints to get Master's data for Cosmetic Product Type & Created Entity Table for Cosmetic Product attribute.
8 | 2026-07-27 | Santhosh Raju | MarketPlace | If I double tap on Send otp button , I got opt 2 times. | In Progress | Present
9 | 2026-07-27 | Amit Hosmani | Pharma Module | Assisted for Billing/ POS UI/UX for selecting customer type (walk-in customer), product search, add product (quantity & unit), billing cart and types of payment capture | Completed | Present
|  |  |  | Working on figma design assistance for invoice preview and sales return | In Progress
10 | 2026-07-27 | Moses | Pharma Module | Creating screens : Purchase Management Flow for existing Products and Billing POS for Walk-in customer | Completed | Present
11 | 2026-07-27 | Somil Merugawar | MarketPlace | Seller User Universal login all seller type implementation work (Seperate Signup first seller Registration Time) | Completed | Present
12 | 2026-07-27 | Dipak | Lab module | Worked on resolving issues in the Super Admin Lab Module Dashboard and ensuring the data is displayed correctly. | Completed | Present
13 | 2026-07-27 | Prabhas K S | Pharma Module | 1)fixed bugs locally (defect no related to user management and setUpBusiness 2) Implemented look and feel of all the category product fields in frontend 3)Integrated masters api for drug and supplement 4) created dto , service and mapper for Cosmetic category 5)tested onboard api for cosmetic category | Completed | Present
14 | 2026-07-27 | Ashik Joshi | Lab Module | 1.Tested the Lab module SuperAdmin and Admin Dashboard | In progress | Present
2.Raised issues for the identified defects and Discussed with Dev and BA.
3.Guided and trained a junior team member on Testing
15 | 2026-07-27 | Sunny | Lab Module | 1.User Management – Enhanced the User Management UI. | Completed | Present
2.Add Lab – Enhanced the Lab Addition UI.
16 | 2026-07-27 | Gowtham | Blood Buddy | Developed a few UI screens for Blood Buddy | In Progress | Present
17 | 2026-07-27 | Shreeraksha | On Leave | On Leave | On Leave | Absent
18 | 2026-07-27 | Archana Jagadish | Uttarakosha | Effort Estimation and Budget Proposal for Uttarakosha | Completed | Present
|  |  | Others |  | Completed

## 28-7-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-08-28 | Nisarga Giri | Training | Worked on bug fixing | In Progress | Present
2 | 28/07/2026 | Shreya M M | Training | Built inventory dashboard with expiry/stock alerts | In Progress | Present
3 | 28/07/2026 | Harshith Gowda | Training | Works on inventory screens | Completed | Present
4 | 28/07/2026 | Basavaraju N N | Pharma Module | Worked on Master Tables Creation and data insertion part for Food and Infant Porduct type and worked on entity/table creation part for Food & Infant Product type. | Completed | Present
|  |  |  | Working on Master tables creation and data insertion part for Consumable medical devices. | In Progress
5 | 2026-07-28 | Prabhas K S | Pharma Module | 1)Master api integration for cosmetic category | Completed | Present
|  |  |  | 2)Master api integration for food and infant category | Completed
|  |  |  | 3) created Dto for food and infant | Completed
|  |  |  | 4)create attribute service and mapper for food and infant | Completed
|  |  |  | 5)api testing & attribute for consumable category | Inprogress
6 | 2026-07-28 | Santhosh Raju | Marketplace | Worked on the OTP functionality. Identified an issue where double-clicking the Send OTP button triggered two OTP requests and resulted in receiving two OTPs.(Email part only). | Completed | Present
7 | 28/07/2026 | Shreeraksha | Pharma Module | Worked on Frontend of Goods Recipt List | Completed | Present
|  |  |  | Worked on Frontend of Confirmation Popup | Completed
8 | 28/07/2026 | Moses | Pharma Module | refining screens : Purchase Management Flow for existing Products and Billing POS for Walk-in customer | Completed | Present
9 | 28/07/2026 | Sunny | Lab Module | Super Admin Dashboard – Bug fixed. | Completed | Present
Admin Dashboard – Modified the frontend to accommodate changes in the backend APIs .
10 | 2026-07-28 | Rajani.I.R | Team building activity | Movie time |  | Present
11 | 2026-07-28 | Dipak | Lab Module | Worked on fixing bugs in the Lab Module Admin Dashboard, specifically in the Test by Categories and Top Ordered Tests sections. | Completed | Present
12 | 2026-07-28 | Ashik Joshi | Lab Module | 1.Tested the Lab module workflow and Admin Dashboard | Completed | Present
2.Raised issues for the identified defects and Discussed with Dev and BA.
3.Guided and trained a junior team member on Testing
13 | 2026-07-28 | Somil Merugawar | MarketPlace | Seller Universal Sign-Up: Implemented validation-related changes for the post-login service today. | Completed | Present
|  |  |  | Implemented user validation changes for the Sign-Up After Admin Approval flow. | Completed
14 | 2026-07-28 | S J Yasshraj Vijayan | Lab Module | Package Management screens | Completed | Present
|  |  |  | Website requirements and UI revamp | In Progress
15 | 2026-07-28 | Gowtham T | Blood Buddy App | 1. Worked on Blood Center Registeration screen UI design. | Completed | Present
|  |  | (Blood Center Registartion) | 2. Package installed and configuration.

## 29-7-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-07-29 | Rajani.I.R | Pharma Inventory | Writing testcases for product goods receipt screen | Completed | Present
|  |  | Lab module | 1.End to end testing | Completed
|  |  |  | 2.Discussion with the team on lab module enhancement | Completed
|  |  |  | 3.Discussion with team on lab issue in production environment | Completed
|  |  |  | 4.Bugs raised were reviewed and retested | In progress
2 | 2026-07-29 | Prabhas K S | Pharma Inventory | 1)Created attribute for consumables and non consumable 2)created service impl and mapper for consumable and non consumable 3) integrated masters api for consumable and non consumable category 4)api testing on consmuable and non consumable attribute 5)helped Roshani for debugging on dahboard rerouting (suspected antivirus problem) | 1 to 4) Completed 5)Inprogress | Present
3 | 2026-07-29 | Basavaraju N N | Pharma Inventory | Worked on consumable/non-consumable master table creation & data insertion and entity creation part. | Completed | Present
|  |  |  | Working on frontend product inventory/ stock expiry status page | In progress
4 | 2026-07-29 | Nisarga Giri | Training | Working on fixing the bugs in the MarketPlace project | In progress | Present
5 | 2026-07-29 | Harshith Gowda | Training | tested inventory screens | completed | Present
6 | 2020-07-29 | Shreya M M | Training | Implemented and tested the automated email alert workflow for inventory expiry and stock notifications | Completed | Present
7 | 2026-07-29 | Shreeraksha | Pharma Module | Worked on the Inventory and Inventory Audit Logs Flow | Completed | Present
Worked on the Purchase and Purchase Details APIs
8 | 2026-07-29 | Roshni Mohan | Pharma Module | working on fixing the bugs | In progress | Present
9 | 2026-07-29 | Santhosh Raju | Marketplace | Worked on debugging the issue. | In progress | Present
10 | 2026-07-29 | Moses | Pharma Module | Creating screens : Product Maintenance, Central Warehouse Details, User Management | In progress | Present
11 | 2026-07-29 | Ashik Joshi | Lab Module | 1.Tested the Lab module workflow and Admin Dashboard | Completed | Present
2.Raised issues for the identified defects and Discussed with Dev and BA.
3.Guided and trained a junior team member on Testing
12 | 2026-07-29 | Dipak | Lab Module | Worked on fixing issues in the Sample Collection and Funnel Chart data in the Lab Module Admin Dashboard. | Completed | Present
13 | 2026-07-29 | Sunny | Lab Module | Sample Managment – Bug fixed related with "widal test". | Completed | Present
Admin Dashboard – Modified the frontend to accommodate changes in the backend APIs & Bug fixed.
Demonstrated all the UI enhancements implemented in the Lab Module to the team.
14 | 2026-07-29 | Somil Merugawar | MarketPlace | Resolve Seller Signup session management related issues | Completed | Present
|  |  |  | Resolved bugs and updated fields related to product addition and seller registration | Completed
15 | 2026-07-29 | Amit Hosmani | Pharma Inventory | Research on adding warehouse management concept (capturing details of warehouse) in the Inventory software to allocate the products for it's peripheral Pharmacies (based on request raised in offline) | Completed | Present
16 | 2026-07-29 | Archana Jagadish | Uttarakosha | Hardware and Software Cost Proposal | Completed | Present
|  |  | Others | Discussions, Meetings, Emails | Completed
17 | 2026-07-29 | S J Yasshraj Vijayan | Lab module, website | Website designs and meeting with Rajesh, Zain. Lab module discussions. | In progress | Present
18 | 2026-07-29 | Gowtham T | Blood Buddy App | 1. Working on it Verify OTP screen UI design. | Completed | Present
|  |  | (Blood Center Registartion) | 2. Worked on Validation and error showing functionalities.
19 | 2026-07-29

## 30-7-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-07-30 | Rajani.I.R | Pharma Marketplace | Testing with respect to login & seller registration is done and testing observations are noted | Completed | Present
|  |  | Pharma Inventory | 1.Writing testcases for Goods receipt screen | Completed
|  |  |  | 2.Writing testcases for Add new purchase screen | Completed
|  |  |  | 3. Writing testcases for Add items to invoice screen | Completed
|  |  |  | 4.Writing testcases for drugs onboarding | Inprogress
|  |  | Lab Module | Retesting of fixed bugs | Completed
|  |  | Lab support | Adding test references for Dengue test in Cureplus Martalli hospital | Completed
2 | 2026-07-30 | Harshith Gowda | Training | 1, Worked on marketplace raise a bug | In progress | Present
|  |  |  | 2, Tested inventary screens | Completed
3 | 2026-07-30 | Gowtham T | Blood Buddy App | 1. OTP Entery Package Installed and configuration setup. | Completed | Present
|  |  | (Blood Center Registartion) | 2. Worked on Login Screen UI design and validation checkup.
4 | 2026-07-30 | Nisarga Giri | Training | Research on product return workflow and billing process | In progress | Present
5 | 2026-07-30 | Archana Jagadish | Others | Uttarakosha requirements document, meetings, task assignments | Completed | Present
6 | 2026-07-30 | Shreya M M | Training | Added Excel file generation for alert logs and updated the dashboard search bar functionality | Completed | Present
7 | 2026-07-30 | Basavaraju N N | Pharma Inventory | Worked on frontend product inventory/ stock expiry status page. | Completed | Present
|  |  |  | Working on Device Specification master table creation and data insertion part | In progress
8 | 2026-07-30 | Shreeraksha | Pharma Inventory | Multi pharmacy implemented in both frontend and backend | In progress | Present
9 | 2026-07-30 | Prabhas K S | Pharma Inventory | 1)Implemented Tax Invoice front look and feel | Completed | Present
2)Tested all the category product onboard api
3) Validation added for all the product category, [product detials, batch details, packaging details]
10 | 2026-07-30 | Moses | Pharma Module | Creating screens : Warehouse Distribution | Inprogress | Present
11 | 2026-07-30 | Ashik Joshi | Lab Module,MarketPlace | 1.Tested the Lab module and MarketPlace | Inprogress | Present
2.Raised issues for the identified defects and Discussed with Dev and BA.
3.Guided and trained a junior team member on Testing
12 | 2026-07-30 | Sunny | Lab Module | Admin & Super Admin Dashboard – Optimized the dashboard data loading process by resolving performance issues. | Completed | Present
Prepared a detailed document outlining proposed future enhancements for Lab Module to support upcoming development .
13 | 2026-07-30 | Somil Merugawar | MarketPlace | Resolved GST and HSN Code display issue on the Product Details Edit page across all five product categories | Completed | Present
|  |  |  | Fixed the product photos download feature for all product categories | Completed
|  |  |  | Updated the batch selection flow to automatically open Create New Batch when no batches are available | Completed
14 | 2026-07-30 | Amit Hosmani | Pharma Inventory | Requirement finalization of warehouse introduction in Inventory Management and attended internal meetings | Completed | Present
15 | 2026-07-30 | Roshni | Pharma Inventory | Bug Fixing- | Completed | Present
16 | 2026-07-30 | Dipak | Lab Module | Worked on the Detailed Billing Report Grid for the Super Admin and Admin dashboards, ensuring accurate data retrieval and display. | Completed | Present
17 | 2026-07-30 | Santhosh Raju | Marketplace | License Number: The field should accept lowercase input and automatically convert it to uppercase while typing, even when Caps Lock is off | Completed | Present
18 | 2026-07-30 | Yash | Pharma Module | Bug Fixing - Patient Management, Report update | Completed | Present

## 31-7-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-07-30 | Rajani.I.R | Pharma Marketplace | Testing with respect to login & seller registration is done and testing observations are noted | Completed | Present
|  |  | Pharma Inventory | 1.Writing testcases for Goods receipt screen | Completed
|  |  |  | 2.Writing testcases for Add new purchase screen | Completed
|  |  |  | 3. Writing testcases for Add items to invoice screen | Completed
|  |  |  | 4.Writing testcases for drugs onboarding | Inprogress
|  |  | Lab Module | Retesting of fixed bugs | Completed
|  |  | Lab support | Adding test references for Dengue test in Cureplus Martalli hospital | Completed
2 | 2026-07-30 | Harshith Gowda | Training | 1, Worked on marketplace raise a bug | In progress | Present
|  |  |  | 2, Tested inventary screens | Completed
3 | 2026-07-30 | Gowtham T | Blood Buddy App | 1. OTP Entery Package Installed and configuration setup. | Completed | Present
|  |  | (Blood Center Registartion) | 2. Worked on Login Screen UI design and validation checkup.
4 | 2026-07-30 | Nisarga Giri | Training | Research on product return workflow and billing process | In progress | Present
5 | 2026-07-30 | Archana Jagadish | Others | Uttarakosha requirements document, meetings, task assignments | Completed | Present
6 | 2026-07-30 | Shreya M M | Training | Added Excel file generation for alert logs and updated the dashboard search bar functionality | Completed | Present
7 | 2026-07-30 | Basavaraju N N | Pharma Inventory | Worked on frontend product inventory/ stock expiry status page. | Completed | Present
|  |  |  | Working on Device Specification master table creation and data insertion part | In progress
8 | 2026-07-30 | Shreeraksha | Pharma Inventory | Multi pharmacy implemented in both frontend and backend | In progress | Present
9 | 2026-07-30 | Prabhas K S | Pharma Inventory | 1)Implemented Tax Invoice front look and feel | Completed | Present
2)Tested all the category product onboard api
3) Validation added for all the product category, [product detials, batch details, packaging details]
10 | 2026-07-30 | Moses | Pharma Module | Creating screens : Warehouse Distribution | Inprogress | Present
11 | 2026-07-30 | Ashik Joshi | Lab Module,MarketPlace | 1.Tested the Lab module and MarketPlace | Inprogress | Present
2.Raised issues for the identified defects and Discussed with Dev and BA.
3.Guided and trained a junior team member on Testing
12 | 2026-07-30 | Sunny | Lab Module | Admin & Super Admin Dashboard – Optimized the dashboard data loading process by resolving performance issues. | Completed | Present
Prepared a detailed document outlining proposed future enhancements for Lab Module to support upcoming development .
13 | 2026-07-30 | Somil Merugawar | MarketPlace | Resolved GST and HSN Code display issue on the Product Details Edit page across all five product categories | Completed | Present
|  |  |  | Fixed the product photos download feature for all product categories | Completed
|  |  |  | Updated the batch selection flow to automatically open Create New Batch when no batches are available | Completed
14 | 2026-07-30 | Amit Hosmani | Pharma Inventory | Requirement finalization of warehouse introduction in Inventory Management and attended internal meetings | Completed | Present
15 | 2026-07-30 | Roshni | Pharma Inventory | Bug Fixing- | Completed | Present
16 | 2026-07-30 | Dipak | Lab Module | Worked on the Detailed Billing Report Grid for the Super Admin and Admin dashboards, ensuring accurate data retrieval and display. | Completed | Present
17 | 2026-07-30 | Santhosh Raju | Marketplace | License Number: The field should accept lowercase input and automatically convert it to uppercase while typing, even when Caps Lock is off | Completed | Present
18 | 2026-07-30 | Yash | Pharma Module | Bug Fixing - Patient Management, Report update | Completed | Present

## 3-8-2026
Sl. No. | Date | Resource Name | Project Name | Task Details | Status | Resource Attendance
1 | 2026-08-03 | Shreeraksha | Pharma Module | Wrote backend endpoint for GRN No. auto generation | Complete | Present
Disscussed and Wrote Entity Diagram for the Billing and Warehouse Modules
2 | 3/8/2026 | Harshith Gowda | Training | 1,tested on marketplace | In-progress | Present
|  |  |  | 2,Adavance Manual teesting course | Completed
3 | 2026-08-02 | Rajani.I.R | Lab support | Cureplus Yellanduru hospital - edit of test values | Completed | Present
| 2026-08-03 |  | Lab Module | 1.Generating reports for the test data received from Sini mam | Completed
|  |  |  | 2.Discussion with the team on lab features development | Completed
|  |  | Others | 1.July Month attendance report sent to Abdul sir and HR team | Completed
|  |  |  | 2.July month leaves report availed by the team is sent to accounts and HR team | Completed
4 | 2026-08-03 | Nisarga Giri | Training | 1. R & D on Order Returns, Billing and Cancellation workflow for Suppliers, Warehouses, &Pharmacies across different business entities | Completed | Present
2. Researched and documented for Internal Stock transfer in Inventory
5 | 2026-08-03 | Roshni Mohan | Marketplace | Researching on marketplace buyer part | In Progress | Present
6 | 2026-08-03 | Gowtham T | Blood Buddy App | 1. Completed the UI design for the Blood Donor Registration screen. | Completed | Present
|  |  | (Blood Donor Module) | 2. Completed the implementation of all validations and error-handling functionalities for the Blood Donor Registration screen.
8 | 2026-08-03 | Santhosh Raju | Marketplace | Worked on removing auto OTP verification during signup and implemented an Invalid OTP pop-up on failed OTP verification. | In Progress | Present
9 | 2026-08-03 | Shreya M M | Training | Added Recharts pie charts for risk/stock insights and stock trend analysis | In Progress | Present
10 | 2026-08-03 | Basavaraju N N | Pharma Module | Worked on Owner Ship Type dropdown part (Raised in bug sheet). | Completed | Present
Worked on delete pharma draft option in frontend.
Worked on error message for pincode(Raised in bug sheet).
Disscussion on the Billing and Warehouse Modules
11 | 2026-08-03 | Prabhas K S | Pharma Module | 1)Removed GRN field fromUI and updated popup module 2)Updated backend DTO's related to batch and purchase 3)Added new validation (mandatory and non mandatory) fields for all the category products 4)implemented stock update for exsisting batch 5)Disscussion on the Billing and Warehouse Modules 6)tested the flow in test environment | Completed | Present
12 | 2026-08-03 | Ashik Joshi | MarketPlace | 1.Tested the MarketPlace- Product page | Inprogress | Present
2.Raised issues for the identified defects and Discussed with Dev and BA.
3.Guided and trained a junior team member on Testing
13 | 2026-08-03 | Dipak | Marketplace | Resolved bank account validation issues by implementing proper validation for invalid/unrecognized IFSC codes and correcting the account number confirmation validation to display the appropriate mismatch error message on field tab-out. | Completed | Present
14 | 2026-08-03 | Moses | Pharma Module | Creating screens : Warehouse Distribution- receiving stock | Inprogress | Present
15 | 2026-08-03 | Amit Hosmani | Pharma Module | Prepared & shared master data for packaging & order details for all 6 products | Completed | Present
|  |  |  | Research on product return for 1:1 & 1:N entity relationship | In Progress
|  |  |  | Datafields enhancement in warehouse distribution & stock transfer | In Progress
16 | 2026-08-03 | Sunny | Lab Module | Compliance Research – Compiled India's regulatory compliance requirements for lab onboarding, Patient onboarding (consent and age verification for sensitive tests), and mandatory disease reporting into a reference document to support the onboarding compliance rules. | In Progress | Present
17 | 2026-08-03 | Somil Merugawar | MarketPlace | Resolved marketplace Product Details bugs: BUG-44, BUG-45, BUG-42, BUG-40, BUG-35, BUG-36, BUG-37, and BUG-38. | Completed | Present
|  |  |  | Product Management bugs BUG-46, BUG-43, and BUG-41 are currently working | In Progress
18 | 2026-08-03 | Archana Jagadish | Uttarakosha | Job Description for Uttarakosha resources, connected with server hardware providers in Hyderabad | Completed | Present
|  |  | Lab Module | Release 2.0.1 feature identification and Sprint planning | In Progress
|  |  | Others |  | Completed
19 | 2026-08-03 | Yash | Lab Module | Lab Report - AI Clinical Observations | In Progress | Present